## About
10.2 Backlog Management
Planning, governance and tracking
What it is for | Keeps a ranked, living list of outstanding work so the next most valuable item is always visible at the top.
Reach for it when | Reach for it on adaptive work where scope is expected to change and the commitment is to the ordering, not to a fixed set.
Confused with | Backlog management is the ongoing custody of the list; prioritisation is the act of ordering it. Items about re-ranking after new information are prioritisation; items about how the list itself is maintained and drawn from are backlog management.
Tasks | 5.2 Maintain Requirements · 5.3 Prioritize Requirements · 5.4 Assess Requirements Changes
Knowledge areas | 5
The worked example is on the next sheet.

## Worked example
10.2 Backlog Management
Worked example · 480 items, triaged before anything is ranked
State | Items | Action
Need already met by a later release | 152 | Retire, with the release noted
Duplicate of another item | 61 | Merge, keep the earliest reference
Still valid, not reviewed this quarter | 198 | Re-rank
Still valid, reviewed this quarter | 69 | Leave
Total | 480
Prioritisation presumes the list represents current need. This one did not.