## About
10.16 Decision Analysis
Valuation and decision
What it is for | Structures a choice under uncertainty by setting out the options, the criteria, the values and the trade-offs between them.
Reach for it when | Reach for it when a decision is contested, the criteria are not agreed, or the outcome depends on events nobody controls.
Confused with | Decision analysis chooses between options; prioritisation sequences items you have already agreed to do. If nothing is being discarded, it is prioritisation.
Tasks | 7.6 Analyze Potential Value and Recommend Solution · 6.4 Define Change Strategy · 7.5 Define Design Options
Knowledge areas | 6, 7
The worked example is on the next sheet.

## Worked example
10.16 Decision Analysis
Worked example · Four metering approaches, criteria weighted before scoring
Criterion | Weight | Smart | Staged | Manual+ | AMI-lite
Regulatory exposure | 35% | 5 | 4 | 1 | 4
Total cost | 25% | 2 | 4 | 5 | 3
Customer disruption | 20% | 2 | 4 | 5 | 3
Speed to comply | 20% | 3 | 3 | 2 | 5
Weighted total | 100% | 3.25 | 3.80 | 2.90 | 3.80
Staged and AMI-lite tie. That is a useful result: the argument moves to a tiebreak the group can have.