10.19  Estimation

Valuation and decision

What it is for

Produces a forecast of cost, effort, duration or value, together with the confidence and assumptions attached to it.

Reach for it when

Reach for it when a decision needs a number that does not yet exist, and the honest answer is a range rather than a point.

Most often confused with

Estimation forecasts an unknown; financial analysis works on figures you already have. An item that hands you cash flows and asks what they are worth is financial analysis.

WORKED EXAMPLE

Claims replacement analysis effort, three-point

| Component | Optimistic | Likely | Pessimistic | Expected |
| --- | --- | --- | --- | --- |
| Rules engine | 30 | 45 | 90 | 50.0 |
| Interfaces | 20 | 25 | 40 | 26.7 |
| Reporting | 10 | 12 | 18 | 12.7 |
| Migration | 15 | 20 | 60 | 25.8 |
| Total (days) | 75 | 102 | 208 | 115.2 |

Expected = (O + 4M + P) / 6. Reporting the 102 understates by 13 days and hides a range of 75 to 208.

Tasks that use it: 3.1 Plan Business Analysis Approach  ·  5.3 Prioritize Requirements  ·  6.4 Define Change Strategy

CBAP® Technique Pack · BABOK® Guide v3 · business-analyst.services · not affiliated with IIBA®