## About
10.19 Estimation
Valuation and decision
What it is for | Produces a forecast of cost, effort, duration or value, together with the confidence and assumptions attached to it.
Reach for it when | Reach for it when a decision needs a number that does not yet exist, and the honest answer is a range rather than a point.
Confused with | Estimation forecasts an unknown; financial analysis works on figures you already have. An item that hands you cash flows and asks what they are worth is financial analysis.
Tasks | 3.1 Plan Business Analysis Approach · 5.3 Prioritize Requirements · 6.4 Define Change Strategy
Knowledge areas | 3, 5, 6
The worked example is on the next sheet.

## Worked example
10.19 Estimation
Worked example · Claims replacement analysis effort, three-point
Component | Optimistic | Likely | Pessimistic | Expected
Rules engine | 30 | 45 | 90 | 50.0
Interfaces | 20 | 25 | 40 | 26.7
Reporting | 10 | 12 | 18 | 12.7
Migration | 15 | 20 | 60 | 25.8
Total (days) | 75 | 102 | 208 | 115.2
Expected = (O + 4M + P) / 6. Reporting the 102 understates by 13 days and hides a range of 75 to 208.