## Slide 1
10.26 Item Tracking
Planning, governance and tracking
WORKED EXAMPLE
CBAP® Technique Pack · BABOK® Guide v3 · business-analyst.services
10.26
WHAT IT IS FOR
Captures and follows issues, risks, conflicts and actions through to resolution, with an owner and a status on each.
REACH FOR IT WHEN
Reach for it when things raised in sessions keep going missing, and the failure is one of follow-through rather than analysis.
MOST OFTEN CONFUSED WITH
Item tracking manages open items; risk analysis assesses and responds to risk. A raised concern with no owner is an item; a quantified threat with a response strategy is a risk.
Tasks: 4.5 Manage Stakeholder Collaboration · 5.4 Assess Requirements Changes · 3.5 Identify Business Analysis Performance Improvements
Nineteen concerns raised in four months
Raising something and watching nothing happen teaches people not to raise things.
Raised | Concern | Type | Owner | Status
12 Mar | Assessors not consulted on field order | Issue | D. Nguyen | Closed
19 Mar | Duplicate-check rule undefined | Issue | — | No owner, 5 months
02 Apr | Cutover may land in peak | Risk | Moved to register | Open
23 Apr | Who signs off migration mapping? | Question | — | No owner, 4 months
07 May | Legacy report parity not agreed | Issue | — | No owner, 3 months