## About
10.27 Lessons Learned
Planning, governance and tracking
What it is for | Assembles what worked, what did not and what should change, from the people who were there, while it is still recoverable.
Reach for it when | Reach for it at the close of a phase or effort, and when the same failure has now happened more than once.
Confused with | Lessons learned improves how the work is done next time; retrospective performance assessment of business analysis itself sits under task 3.5. The technique is the session, the task is the accountability.
Tasks | 3.5 Identify Business Analysis Performance Improvements · 8.5 Recommend Actions to Increase Solution Value
Knowledge areas | 3, 8
The worked example is on the next sheet.

## Worked example
10.27 Lessons Learned
Worked example · Held before the team rolled off, not after the benefits data matured
Block | Content
What worked | Co-located analysts and testers Weekly stakeholder demo held every week without exception
What did not | Requirements churn ran at 3x the norm Same pattern on the prior programme, never examined Sign-off authority moved twice, undocumented
Change next time | Name the approver per requirement type at initiation Re-baseline when authority moves, not at phase end Record the reason for change, not just the change
Change records showed what changed. Only the team could say why this programme and its predecessor churned alike.