## About
10.33 Prioritisation
Planning, governance and tracking
What it is for | Orders requirements or work against agreed bases such as value, cost, risk, dependency, regulatory deadline or implementation difficulty.
Reach for it when | Reach for it whenever demand exceeds capacity, which is nearly always, and the sequence has to be defensible to people who lose out.
Confused with | Prioritisation orders things you intend to do; decision analysis picks between options where some are discarded. Also watch the basis: an item where a regulatory date is in play is not decided by value.
Tasks | 5.3 Prioritize Requirements · 5.4 Assess Requirements Changes · 6.4 Define Change Strategy
Knowledge areas | 5, 6
The worked example is on the next sheet.

## Worked example
10.33 Prioritisation
Worked example · Superannuation release — sequenced on constraint, not value
Value \ Effort | Low | High
High | DO FIRST ON VALUE Member portal redesign | Adviser dashboard
Low | Data quality fix | Legislative change
Value alone puts the portal first. The data fix is a dependency of the legislative change, and the legislative change has a 1 July date with a licence condition attached. Sequence: data fix, legislative change, then the portal.