## About
10.36 Prototyping
Elicitation and collaboration
What it is for | Makes an early, partial version of the solution so stakeholders can react to something concrete instead of describing something abstract.
Reach for it when | Reach for it when requirements are unclear because people cannot picture the outcome, or when a technical assumption needs testing before commitment.
Confused with | A prototype elicits and validates; it is not the solution and not a design specification. Items where the prototype quietly becomes the build are testing whether you know the difference between throwaway and evolutionary intent.
Tasks | 4.2 Conduct Elicitation · 7.5 Define Design Options · 7.3 Validate Requirements
Knowledge areas | 4, 7
The worked example is on the next sheet.

## Worked example
10.36 Prototyping
Worked example · Claims intake screen, three rounds in nine days
# | Stage | Step | Detail
1 | Round 1 | Paper sketch | Field order disputed by 4 of 6 assessors
2 | Round 2 | Clickable, 1 screen | Reveals the missing duplicate-claim check
3 | Round 3 | Clickable, 4 screens | Agreed; requirements written from it
4 | Then | Discarded | No error handling, no security model, no tests
| exception | Discarded | — throwaway by intent. Deciding to extend it later is a different decision, made once.