## About
10.38 Risk Analysis and Management
Valuation and decision
What it is for | Identifies uncertain events that could affect value, assesses their likelihood and impact, and settles a response for each.
Reach for it when | Reach for it when the change strategy depends on things nobody controls, and unnamed risk is being carried as optimism.
Confused with | A risk is an uncertain future event; an issue is already happening and belongs in item tracking. And the responses are avoid, transfer, mitigate, accept or increase, not simply escalate.
Tasks | 6.3 Assess Risks · 6.4 Define Change Strategy · 3.1 Plan Business Analysis Approach
Knowledge areas | 3, 6
The worked example is on the next sheet.

## Worked example
10.38 Risk Analysis and Management
Worked example · Migration risks, post-mitigation, with residual exposure named
Likelihood \ Impact | Moderate | Major | Severe
Likely | Data quality rework | — | —
Possible | Training slippage | EMV $87,500 Limited remediation | —
Unlikely | — | Vendor resourcing | EMV $135,000 Severe remediation
Expected monetary value across all outcomes is $222,500. That figure goes in the business case; the $900,000 severe case goes here.