10.41  Scope Modelling

Modelling and specification

What it is for

Draws the boundary of the change: what is inside, what is outside, and what sits on the edge.

Reach for it when

Reach for it when scope is contested, when the effort keeps absorbing adjacent work, or before any credible estimate can be given.

Most often confused with

Scope modelling sets the boundary; interface analysis specifies what crosses it; functional decomposition breaks down what is inside. Boundary disputes are scope.

WORKED EXAMPLE

Licensing modernisation, after three informal absorptions

| Block | Content |
| --- | --- |
| In scope | Licence application and renewal Eligibility assessment Fee calculation and payment Public register of licences |
| Out of scope | Complaints handling Inspections scheduling Prosecution case management Finance general ledger |
| Adjacent — decide before it drifts | Inspection outcomes feeding eligibility Register data reused by complaints Shared identity for licence holders |

Tasks that use it: 6.2 Define Future State  ·  6.4 Define Change Strategy  ·  7.4 Define Requirements Architecture

CBAP® Technique Pack · BABOK® Guide v3 · business-analyst.services · not affiliated with IIBA®