## The chain
One scenario, sixteen techniques
Fairgate Roads Authority — heavy vehicle access permits
Step | Technique | Takes | Gives
1 | 10.43 Stakeholder List, Map, or Personas | Nothing — this is the first pass. | Eight parties positioned by influence and interest. Road managers turn out to hold a veto nobody had planned around.
2 | 10.18 Document Analysis | The stakeholder list, which says who owns which document. | What is already settled, and the three questions only a person can answer. Those become the interview guide.
3 | 10.31 Observation | The two unexplained checks from the document analysis. | The real practice, including a shortcut nobody had documented. Feeds the current-state process model.
4 | 10.35 Process Modelling | The observed practice, not the documented procedure. | Four stages and the hand-offs between them. These four stage names are used unchanged by every later step.
5 | 10.34 Process Analysis | The four stages from the process model, by the same names. | Elapsed against touch time, and a cost to serve of $41 a permit. Both are consumed by the business case.
6 | 10.40 Root Cause Analysis | The worst row of the process analysis. | A cause that is about data, not effort. That rules out the obvious option before it is costed.
7 | 10.20 Financial Analysis | The $41 cost to serve, and the root cause that says more assessors will not help. | Three options valued over five years at 7%. B has the best NPV, C the fastest payback.
8 | 10.16 Decision Analysis | The NPV and payback figures, unchanged. | A recommendation with the weighting visible, so the argument is about criteria rather than preference.
9 | 10.38 Risk Analysis and Management | The recommended option, and the road manager veto from the stakeholder map. | An expected monetary value of $196,000, which goes into the business case beside the benefit.
10 | 10.7 Business Cases | Need, options, value, risk — each already produced by a step above. | An approved change strategy. Nothing new is invented here; the case is an assembly.
11 | 10.41 Scope Modelling | The approved change strategy. | A boundary. The in-scope list becomes the top level of the decomposition, unchanged.
12 | 10.22 Functional Decomposition | The four in-scope items, as the top level. | Functions small enough to specify. 'Assess route' is where the rules and the data live.
13 | 10.9 Business Rules Analysis | The 'Assess route' function. | Rules held apart from the process. Each names the data elements it needs, which sets the dictionary.
14 | 10.12 Data Dictionary | The data column of the rules table. | Element definitions precise enough to build and to migrate.
15 | 10.44 State Modelling | The process stages and the refusal rule. | Permitted transitions, including two that must be forbidden.
16 | 10.28 Metrics and Key Performance Indicators | The benefits claimed in the business case, and the states just defined. | Measures with targets and the threshold at which someone must act. This is what closes the loop back to step 5.
Sixteen techniques, each taking something the one before it produced. Nothing here is a fresh start: the process model becomes the analysis rows, the worst row becomes the root cause, the cost to serve becomes the business case, the scope becomes the functions, the functions become the rules and the use cases, and the benefit becomes the KPI. That chain is what makes a technique useful — on its own each is a drawing, in sequence they are an argument.

## 01 10.43
Step 1 · 10.43 Stakeholder List, Map, or Personas
Who is affected, and who actually decides?
Takes: Nothing — this is the first pass.
Gives: Eight parties positioned by influence and interest. Road managers turn out to hold a veto nobody had planned around.
Who matters, and how much
Influence \ Interest | Low | High
High | KEEP SATISFIED Transport regulator Fairgate executive | MANAGE CLOSELY Road managers (11 councils) Permit assessors Freight operators
Low | Finance | KEEP INFORMED Police heavy vehicle unit Bridge engineering
Road managers are external to Fairgate and consent individually. That is the first sign the 15-day obligation is not entirely within Fairgate's control.

## 02 10.18
Step 2 · 10.18 Document Analysis
What do the existing artefacts already answer?
Takes: The stakeholder list, which says who owns which document.
Gives: What is already settled, and the three questions only a person can answer. Those become the interview guide.
Read before anyone's time is booked
Source | What it settled | What it could not
National scheme instrument | 15 days, routine applications only | What counts as routine
Assessment procedure v4 | The 6 documented checks | Why 2 of them are skipped at volume
Consent deed, 11 councils | Each council has 10 business days | Whether that runs concurrently or in series
Permit system specification | Fields captured at lodgement | Whether route data is reliable enough to automate
The consent question matters most: 11 councils at 10 days in series cannot fit inside 15 days at all.

## 03 10.31
Step 3 · 10.31 Observation
What do assessors actually do, as opposed to what the procedure says?
Takes: The two unexplained checks from the document analysis.
Gives: The real practice, including a shortcut nobody had documented. Feeds the current-state process model.
Six documented checks, watched across nine applications
Documented check | Observed | Gap
1. Vehicle configuration | Done every time | None
2. Mass limits | Done every time | None
3. Bridge capacity | Skipped when the route is 'known' | 'Known' is the assessor's memory, not a register
4. Road manager list | Done every time | None
5. Seasonal load restriction | Skipped in 7 of 9 | Restriction data sits in a separate system nobody opens
6. Prior refusal check | Done every time | None
Two of the six checks rely on recall rather than data. Both are the checks that generate rework when a road manager objects.

## 04 10.35
Step 4 · 10.35 Process Modelling
What is the end-to-end flow, and where does it change hands?
Takes: The observed practice, not the documented procedure.
Gives: Four stages and the hand-offs between them. These four stage names are used unchanged by every later step.
Current state — application to permit
Lane | Step 1 | Step 2 | Step 3 | Step 4 | Step 5
Operator | Lodge application
Assessor |  | Lodgement check | Route assessment
Road managers |  |  |  | Road manager consent
Registry |  |  |  |  | Permit issue
exception |  |  |  | objection — reassess, and the clock restarts → step 3
exception |  | incomplete — returned to operator → step 1
Consent sits in a lane Fairgate does not own. Every objection returns the file to assessment and restarts the elapsed clock.

## 05 10.34
Step 5 · 10.34 Process Analysis
Where do the 40 days actually go?
Takes: The four stages from the process model, by the same names.
Gives: Elapsed against touch time, and a cost to serve of $41 a permit. Both are consumed by the business case.
40 days elapsed, 3.2 hours of work
Stage | Elapsed | Touch time | Verdict
Lodgement check | 4 days | 0.3 h | Queue
Route assessment | 19 days | 2.1 h | Queue, plus rework from objections
Road manager consent | 14 days | 0.4 h | Outside Fairgate, 11 councils in series
Permit issue | 3 days | 0.4 h | Queue
Total | 40 days | 3.2 h | Touch time is 1.1% of elapsed
Cost to serve is $41 a permit across 12,000 permits, so $492,000 a year. Adding assessors buys touch time, which is 1.1% of the problem.

## 06 10.40
Step 6 · 10.40 Root Cause Analysis
Why does route assessment take 19 days to do 2.1 hours of work?
Takes: The worst row of the process analysis.
Gives: A cause that is about data, not effort. That rules out the obvious option before it is costed.
Why route assessment runs to 19 days
Level | Item | Note
Symptom | Route assessment takes 19 days for 2.1 hours of work
Why | Why? Files wait to be reworked after objections
Why again | Why? Road managers object to routes already assessed
Root cause | Bridge and seasonal restriction data is not on the assessor's screen
Why | Why? Assessors batch work to avoid switching systems
Why again | Why? Restriction data lives in a second system
Root cause | The same root: the data an assessment needs is not where the assessment happens
Both branches end in the same place, which is what makes it a root cause rather than two problems.

## 07 10.20
Step 7 · 10.20 Financial Analysis
What is each option worth?
Takes: The $41 cost to serve, and the root cause that says more assessors will not help.
Gives: Three options valued over five years at 7%. B has the best NPV, C the fastest payback.
Three options, five years, discounted at 7%
Option | Cost per permit | Annual saving | Investment | NPV | Payback
A More assessors | $41 | ($180,000) | $120,000 | ($858,036) | never
B Rules engine and self-service | $19 | $264,000 | $700,000 | $382,452 | 2.65 yrs
C Outsource assessment | $31 | $120,000 | $250,000 | $242,024 | 2.08 yrs
Option A is the one the executive asked for. It adds touch-time capacity to a queue problem and returns a negative NPV, which is exactly what the root cause predicted.

## 08 10.16
Step 8 · 10.16 Decision Analysis
B has the better return and C pays back sooner. Which?
Takes: The NPV and payback figures, unchanged.
Gives: A recommendation with the weighting visible, so the argument is about criteria rather than preference.
Weighted against criteria agreed before scoring
Criterion | Weight | A | B | C
Meets the 15-day obligation | 40% | 1 | 5 | 3
Five-year value | 25% | 1 | 5 | 4
Cash exposure | 15% | 4 | 2 | 4
Keeps assessment capability in house | 20% | 5 | 5 | 1
Weighted total | 100% | 2.25 | 4.55 | 2.95
C pays back faster and still loses, because payback carries 15% of the decision and the statutory obligation carries 40%. Naming the weights first is what stops that being an argument about opinions.

## 09 10.38
Step 9 · 10.38 Risk Analysis and Management
What could stop option B working?
Takes: The recommended option, and the road manager veto from the stakeholder map.
Gives: An expected monetary value of $196,000, which goes into the business case beside the benefit.
Option B risks, post-mitigation
Likelihood \ Impact | Moderate | Major | Severe
Likely | Assessor adoption
Possible | Restriction data quality | EMV $126,000 Councils decline to consent digitally
Unlikely |  | EMV $70,000 Scheme rules change before go-live
Expected monetary value across all outcomes is $196,000. That figure enters the business case; the severe cases stay here.

## 10 10.7
Step 10 · 10.7 Business Cases
Is the change justified, and on what?
Takes: Need, options, value, risk — each already produced by a step above.
Gives: An approved change strategy. Nothing new is invented here; the case is an assembly.
The case for option B
Block | Content
Need | 15-day statutory obligation from 1 July 40 days today, 1.1% of it working time $492,000 a year to serve
Options considered | A more assessors — negative NPV C outsource — faster payback, loses capability B rules engine and self-service — recommended Do nothing — non-compliant
Value | $264,000 a year saved $382,452 NPV over five years Cost per permit $41 to $19
Risk | Expected monetary value $196,000 Largest: councils declining digital consent
Timing | Must be live before 1 July Consent redesign is on the critical path
What success looks like | Routine permits decided in 15 days Measured, not asserted — see step 16

## 11 10.41
Step 11 · 10.41 Scope Modelling
What is in, what is out, and what will try to creep in?
Takes: The approved change strategy.
Gives: A boundary. The in-scope list becomes the top level of the decomposition, unchanged.
Boundary for the permit service change
Block | Content
In scope | Application lodgement Route assessment Road manager consent Permit issue and variation
Out of scope | Enforcement and infringements Bridge asset management Operator accreditation Fee setting
Adjacent — decide before it drifts | Restriction data mastering Council consent portal Registry identity
Restriction data is adjacent and unavoidable: the root cause sits in it. Naming it here forces the decision rather than absorbing it silently.

## 12 10.22
Step 12 · 10.22 Functional Decomposition
What does the in-scope work break into?
Takes: The four in-scope items, as the top level.
Gives: Functions small enough to specify. 'Assess route' is where the rules and the data live.
The permit service, broken down far enough to specify
Level | Item | Note
Service | Issue a heavy vehicle access permit
Function | Lodge application
Sub-function | Capture vehicle configuration
Sub-function | Capture proposed route
Function | Assess route
Sub-function | Check mass and bridge limits
Sub-function | Check seasonal restrictions
Sub-function | Determine affected road managers
Function | Obtain consent
Sub-function | Request consent
Sub-function | Track and escalate
Function | Issue and vary
Sub-function | Issue permit
Sub-function | Vary or revoke

## 13 10.9
Step 13 · 10.9 Business Rules Analysis
What governs an assessment, and how often will it change?
Takes: The 'Assess route' function.
Gives: Rules held apart from the process. Each names the data elements it needs, which sets the dictionary.
Assessment rules, governed separately from the workflow
Rule | Statement | Data it needs | Owner
ASR-01 | A route crossing a bridge below the vehicle's gross mass is refused. | bridge_capacity_t, gross_mass_t | Bridge engineering
ASR-02 | A route under a seasonal restriction is refused for the restricted dates. | restriction_from, restriction_to | Road managers
ASR-03 | An application matching a refusal within 12 months goes to panel. | prior_refusal_date | Policy
ASR-04 | Consent is required from every road manager on the route. | road_manager_id | Policy
The scheme rules changed twice last year. Held in workflow code each change is a release; held here each change is a rule version.

## 14 10.12
Step 14 · 10.12 Data Dictionary
What exactly are the elements those rules depend on?
Takes: The data column of the rules table.
Gives: Element definitions precise enough to build and to migrate.
Elements the assessment rules depend on
Element | Meaning | Type | Permitted | Mandatory
gross_mass_t | Total mass of vehicle and load | Decimal | > 0, one decimal | Yes
bridge_capacity_t | Rated capacity of a structure on the route | Decimal | > 0, one decimal | Yes
restriction_from | First day a seasonal restriction applies | Date | Not before today | No
restriction_to | Last day it applies | Date | ≥ restriction_from | No
road_manager_id | The council or authority controlling a road segment | Reference | One of 11 | Yes
prior_refusal_date | Date of the most recent refusal for this operator and route | Date | Not future-dated | No
restriction_from and restriction_to are the elements the observed shortcut skipped. Defining them is what moves the check from memory to data.

## 15 10.44
Step 15 · 10.44 State Modelling
What may a permit become, and from where?
Takes: The process stages and the refusal rule.
Gives: Permitted transitions, including two that must be forbidden.
Permit lifecycle
From | Event | To | Permitted
Lodged | assessed | Assessed | yes
Assessed | consent sought | Consent pending | yes
Consent pending | all consents in | Issued | yes
Assessed | refused | Refused | yes
Issued | revoked | Revoked | yes
Consent pending | objection, reassess | Assessed | yes
Refused | issued after refusal | Issued | NO — forbidden
Revoked | reinstated after revocation | Issued | NO — forbidden
The objection loop back to Assessed is the one the process model showed restarting the clock. It is legal, and it is the thing the 15-day obligation cannot absorb twice. Terminal states: Refused, Revoked.

## 16 10.28
Step 16 · 10.28 Metrics and Key Performance Indicators
How will anyone know whether it worked?
Takes: The benefits claimed in the business case, and the states just defined.
Gives: Measures with targets and the threshold at which someone must act. This is what closes the loop back to step 5.
From the obligation down to the indicator someone acts on
Level | Item | Note
Objective | Decide routine permits within 15 days at $19 a permit
Strategy | Remove the queue in assessment
Tactic | Put restriction and bridge data on the assessment screen
KPI | Median days Lodged to Issued — target ≤ 15, act above 13 | lagging
KPI | Objection rate — target ≤ 6%, act above 9% | leading
Strategy | Shorten consent
Tactic | Seek consent from all road managers at once
KPI | Median consent days — target ≤ 7, act above 9 | lagging
KPI | Councils consenting digitally — target ≥ 9 of 11, act below 7 | leading
Baseline is step 5: 40 days, $41 a permit. Without that row there is no improvement to claim, only an assertion.